## README
CopyMe (CpM) — Sprint Tracker
Companion to: COPYME_SPRINT_PLAN.md
Owners: Paul Pereira (US) · Jože Kralj (SI)
Plan date: 2026-05-09
How to use this tracker
• Each row in the 'Sprints' tab is a 1-hour Claude Code unit of work.
• Set Status to: todo → in_progress → done (or blocked).
• 'Owner' is who is executing the sprint right now.
• 'Acceptance' is the canonical pass/fail; mirrors the AC in the markdown plan.
• Filter by Phase or Workstream to plan a working session.
• 'Dashboard' tab auto-counts progress.
Phases
Sprint 0 — Close Jože's 2nd-feedback edits (8 sprints)
Phase 1 — Communication core, Year 1 free tier (60 sprints)
Phase 2 — Yogi AI + surveys + ad marketplace + paid tiers (35 sprints)
Phase 3 — Value Account Pay (27 sprints, regulator-gated)
Business — Entity, IP, €1M angel raise, Boscarol track (12 sprints)
Definition of Done
1. Code compiles, type-checks, lints clean.
2. AC verified locally and on Vercel preview where user-visible.
3. New behavior covered by ≥1 automated test.
4. PR titled 'S-XXX: <Title>' against main with 3-line summary.
5. This row marked 'done'.
Feedback 3 update (2026-05-10)
• See FEEDBACK_3_CORRECTION_PLAN.md for the full correction plan and dated timeline.
• 6 new sprints added: S-009 (email migration), S-010 (hero H2), B-013 (use of proceeds), B-014 (investor list), B-015 (timeline), B-016 (customer-ready gate).
• S-001 was corrected — 'Communication That Matters' stays as H1.
• Total backlog: 161 sprints (was 155).
• Target gates: G0 by 2026-05-12 · G1 by 2026-05-22 · G2 by 2026-06-02 · G3 by 2026-06-09.

## Sprints
ID | Phase | Workstream | Sprint title | Goal / Acceptance | Depends on | Owner | Status | Estimate (hr) | Sprint # | Started | Completed | Notes
S-001 | Sprint 0 | PROD | Hero — remove 'Copies', keep 'Communication That Matters' (corrected per Feedback 3) | H1 reads 'Communication That Matters'; 'Copies' string gone; OG regenerated. Feedback 3 clarified Communication That Matters was never meant to be removed. | — |  | todo | 1 |  |  |  | Corrected per Feedback 3 (2026-05-10)
S-002 | Sprint 0 | PROD | Hero subhead Rule of 7 rewrite | Replace subhead per Joze's exact wording; remove old strings. | S-001 |  | todo | 1
S-003 | Sprint 0 | TRUST | Move Rule-of-7 mechanics to Terms | Strip 70/7/last-7 numbers from landing; ensure they live in Terms §3. | S-002 |  | todo | 1
S-004 | Sprint 0 | TRUST | Fix Terms suspension wording + typo | Reword 'We can suspend' line; fix 'suspened' typo. | — |  | todo | 1
S-005 | Sprint 0 | PROD | Logo: drop 'Rule of 7' subscript | Clean SVG mark; regenerate favicons; keep legacy lockup in press kit. | — |  | todo | 1
S-006 | Sprint 0 | PROD | Logo variant: globe-with-figure | Two SVG explorations adding small globe + figure (per original paper). | S-005 |  | todo | 1
S-007 | Sprint 0 | ENG | Add country code +386 (Slovenia) to phone auth | Slovenia selectable, validated, sample SMS sent in dev. | — |  | todo | 1
S-008 | Sprint 0 | PROD | Cross-device live test (US ↔ SI) | Install PWA on Paul + Joze phones; exchange messages; capture screenshots. | S-007; S-001..S-005 deployed |  | todo | 1
S-101 | Phase 1 | ENG | Phone-first sign-up flow | Country code → SMS OTP → display name. | S-007 |  | todo | 1
S-102 | Phase 1 | ENG | Country picker: full ITU list | 240+ entries; SI/US pinned for context; keyboard-navigable. | S-007 |  | todo | 1
S-103 | Phase 1 | ENG | OTP backend (provider-agnostic) | Twilio + fallback behind sendOtp() interface. | S-101 |  | todo | 1
S-104 | Phase 1 | PROD | Onboarding 'first 7 contacts' import | Up to 7; skip allowed; analytics event. | S-101 |  | todo | 1
S-105 | Phase 1 | PROD | Display-name + avatar setup | Required name, optional avatar, default generator. | S-101 |  | todo | 1
S-106 | Phase 1 | ENG | Session management & device list | Sessions table; revoke a device. | S-101 |  | todo | 1
S-107 | Phase 1 | ENG | Refresh-token rotation + replay protection | Single-use refresh; replay alerts user. | S-106 |  | todo | 1
S-108 | Phase 1 | TRUST | Lost-phone recovery flow | Secondary number OR signed recovery file. | S-106 |  | todo | 1
S-109 | Phase 1 | TRUST | Hard-delete account flow | Self-serve delete per Terms §8; 30-day grace + ZIP export. | S-105 |  | todo | 1
S-110 | Phase 1 | TRUST | 16+ age gate at signup | Per-locale digital-consent threshold; block + appeal. | S-101 |  | todo | 1
S-111 | Phase 1 | ENG | Server-side 70-word message cap | Reject >70 with RULE_OF_7_WORD_CAP error. | S-101 |  | todo | 1
S-112 | Phase 1 | ENG | Client live word counter | Counter under composer; amber@60, red@70, hard-stop. | S-111 |  | todo | 1
S-113 | Phase 1 | ENG | 7-item media-group cap | Picker disables +; server rejects >7. | S-101 |  | todo | 1
S-114 | Phase 1 | ENG | 70-second voice/video cap | Recorder hard-stops at 70s. | S-101 |  | todo | 1
S-115 | Phase 1 | ENG | 7 active contacts (free) enforcement | 8th archives least-recent thread. | S-101 |  | todo | 1
S-116 | Phase 1 | ENG | Last-7 messages retention (free) | Hourly pruning job; in-thread upgrade hint. | S-115 |  | todo | 1
S-117 | Phase 1 | ENG | Rule-of-7 telemetry dashboard | Grafana panel; alert if any cap < 0.5% trigger. | S-111..S-116 |  | todo | 1
S-118 | Phase 1 | ENG | Rule-of-7 enforcement integration tests | E2E suite, < 3 min, no flakes. | S-111..S-116 |  | todo | 1
S-121 | Phase 1 | ENG | Inbox list — 7-item view | Virtualized 7-thread inbox; pull-to-refresh. | S-115 |  | todo | 1
S-122 | Phase 1 | ENG | Thread view — bubble layout | Bubbles, separators, read receipts, smooth on mid-tier Android. | S-121 |  | todo | 1
S-123 | Phase 1 | ENG | Composer with n/70 counter | Sticky composer; paste >70 trims with toast. | S-112 |  | todo | 1
S-124 | Phase 1 | ENG | Typing indicator + presence | Opt-out per privacy; defaults documented. | S-122 |  | todo | 1
S-125 | Phase 1 | ENG | Read receipts (opt-out) | Mutual invisibility on opt-out. | S-122 |  | todo | 1
S-126 | Phase 1 | PROD | Reactions limited to 7 emoji | ❤️ 👍 😂 😮 😢 🔥 💜 only. | S-122 |  | todo | 1
S-127 | Phase 1 | PROD | Reply / quote (no forward chains) | Reply inline; forward intentionally absent. | S-122 |  | todo | 1
S-128 | Phase 1 | ENG | Search across last-7 per thread | <100 ms on 7×7 corpus. | S-116 |  | todo | 1
S-129 | Phase 1 | ENG | Push notifications (FCM + APNs) | Per-thread mute, quiet hours, per-device opt-in. | S-122 |  | todo | 1
S-130 | Phase 1 | ENG | Offline send queue | Max 7 queued messages; flush on reconnect. | S-123 |  | todo | 1
S-131 | Phase 1 | ENG | Voice clip recorder (≤70s) | Hold-to-record; waveform; transcript stub. | S-114 |  | todo | 1
S-132 | Phase 1 | ENG | Video clip recorder (≤70s) | 720p; thumbnail; HLS via CDN. | S-114 |  | todo | 1
S-133 | Phase 1 | TRUST | Image attachments (≤7, EXIF stripped) | Server strips EXIF incl. GPS. | S-113 |  | todo | 1
S-134 | Phase 1 | ENG | Document attachments | ≤7 docs, ≤25 MB; PDF preview. | S-113 |  | todo | 1
S-135 | Phase 1 | ENG | Voice/video transcripts (opt-in) | Off by default; sibling of clip. | S-131; S-132 |  | todo | 1
S-136 | Phase 1 | ENG | 1:1 voice call (beta flag) | WebRTC; flag default OFF; 70-min cap. | S-131 |  | todo | 1
S-141 | Phase 1 | TRUST | E2E protocol selection + key gen | Signal Protocol; identity + prekeys at signup. | S-101 |  | todo | 1
S-142 | Phase 1 | ENG | E2E for text messages | Server holds ciphertext only; rotate keys 7d. | S-141 |  | todo | 1
S-143 | Phase 1 | ENG | E2E for media (chunked) | Cross-device decryption test passes. | S-142 |  | todo | 1
S-144 | Phase 1 | TRUST | Safety-number verification | Per-contact safety #; alert on change. | S-142 |  | todo | 1
S-145 | Phase 1 | PROD | Privacy controls screen | Single screen consolidating all opt-outs. | S-124; S-125; S-135 |  | todo | 1
S-146 | Phase 1 | TRUST | Data-export ZIP (GDPR Art.15) | Portable ZIP delivered ≤7 days. | S-109 |  | todo | 1
S-151 | Phase 1 | PROD | Profile screen | Visual parity with mock; deep-linkable settings. | S-105 |  | todo | 1
S-152 | Phase 1 | PROD | Plan card (Free/Pro/Business) | Live tier; CTA → /pricing. | S-151 |  | todo | 1
S-153 | Phase 1 | PROD | Pricing page polish | Lighthouse a11y > 95 on mobile. | — |  | todo | 1
S-154 | Phase 1 | PROD | Press kit polish | ZIP download; legacy + new logos. | S-005 |  | todo | 1
S-155 | Phase 1 | TRUST | Privacy policy refresh | Align with Yogi DPA + EU/UK rights. | — |  | todo | 1
S-156 | Phase 1 | TRUST | Terms diff PR | Consolidate Sprint 0 changes; lawyer-friendly. | S-003; S-004 |  | todo | 1
S-157 | Phase 1 | TRUST | Cookie / tracking banner (EU) | Geo-detected; analytics gated by consent. | S-155 |  | todo | 1
S-158 | Phase 1 | BIZ | Investor data-room polish | /pitch live metrics; cached at edge. | — |  | todo | 1
S-161 | Phase 1 | ENG | PWA install prompt + manifest | Lighthouse PWA score 100. | S-005 |  | todo | 1
S-162 | Phase 1 | ENG | iOS Safari install handoff | UA-detected; one-time dismissable. | S-161 |  | todo | 1
S-163 | Phase 1 | ENG | Capacitor wrapper for stores | Shells build; push wired. | S-129; S-161 |  | todo | 1
S-164 | Phase 1 | PROD | App Store metadata + screenshots | Submitted to TestFlight track. | S-163 |  | todo | 1
S-165 | Phase 1 | PROD | Play Store metadata + screenshots | Listing in Internal Testing. | S-163 |  | todo | 1
S-166 | Phase 1 | ENG | Deep links (copyme://) | Universal + App Links; .well-known served. | S-163 |  | todo | 1
S-171 | Phase 1 | TRUST | Report-message flow | Long-press → Report; 4 reasons; receipt notice. | S-122 |  | todo | 1
S-172 | Phase 1 | TRUST | Block contact | Mutual invisibility; no leak. | S-115 |  | todo | 1
S-173 | Phase 1 | TRUST | NSFW + CSAM hash matching | NCMEC hash-match; perceptual NSFW flag. | S-133 |  | todo | 1
S-174 | Phase 1 | TRUST | Anti-spam heuristics | Rate, novel-recipient ratio, link density. Precision >0.9. | S-115 |  | todo | 1
S-175 | Phase 1 | TRUST | Account suspension flow | Soft → hard suspend; appeal email; Terms §4 verbatim. | S-004 |  | todo | 1
S-176 | Phase 1 | TRUST | Transparency report scaffold | Quarterly template + pipeline. | S-175 |  | todo | 1
S-181 | Phase 1 | ENG | Structured logging baseline | JSON logs to Vercel + long-term store. | — |  | todo | 1
S-182 | Phase 1 | ENG | Error tracking (Sentry) | Release-tagged; PII scrubbed. | S-181 |  | todo | 1
S-183 | Phase 1 | ENG | RUM (Core Web Vitals) | LCP < 2.5s p75 on landing. | S-181 |  | todo | 1
S-184 | Phase 1 | ENG | Synthetic monitoring | 5-min checks; alert on 2 fails; status page. | S-181 |  | todo | 1
S-185 | Phase 1 | ENG | Backup + DR drill (7-day RPO) | Documented restore drill executed. | — |  | todo | 1
S-186 | Phase 1 | ENG | Feature flags wrapper | Wrap flag SDK; first 2 flags live, default OFF. | — |  | todo | 1
S-187 | Phase 1 | ENG | CI/CD: preview-per-PR + main → prod | Branch protections; required checks. | — |  | todo | 1
S-188 | Phase 1 | ENG | Load test 1k → 10k | p95 signup <600 ms; 5xx <0.1%. | S-101; S-122 |  | todo | 1
S-191 | Phase 1 | PROD | Beta cohort: invite first 70 | Curated invite; thank-you banner. | S-187; S-188 |  | todo | 1
S-192 | Phase 1 | TRUST | Public launch checklist sign-off | Legal/security/a11y/perf signed. | S-176; S-184 |  | todo | 1
S-193 | Phase 1 | BIZ | Press / partnerships outreach | 7 SI + 7 US outlets; 2 podcasts pre-briefed. | S-154 |  | todo | 1
S-194 | Phase 1 | PROD | Phase 1 LAUNCH day | Public; war-room rotating Paul/Joze/Claude. | S-191; S-192; S-193 |  | todo | 1
S-201 | Phase 2 | ENG | Yogi conversational shell | Yogi entry in inbox; consent before any cleartext leaves device. | S-122 |  | todo | 1
S-202 | Phase 2 | PROD | Yogi suggestion chip | 'Yogi suggests' chip above composer (per mock). | S-201 |  | todo | 1
S-203 | Phase 2 | TRUST | Yogi subprocessor + DPA | Choose AI vendor; sign DPA; Privacy update. | S-201 |  | todo | 1
S-204 | Phase 2 | ENG | Yogi cost meter + budget guard | Daily token budget; soft cap @70%. | S-201 |  | todo | 1
S-205 | Phase 2 | TRUST | Yogi safety filters | PII/hate/self-harm/CSAM filters; red-team passes. | S-201 |  | todo | 1
S-206 | Phase 2 | ENG | Yogi memory (per-thread, opt-in) | Memory wipe on opt-out; user can audit. | S-201 |  | todo | 1
S-207 | Phase 2 | PROD | Yogi smart replies (3 options) | Each ≤70 words; analytics on accept/decline. | S-202 |  | todo | 1
S-208 | Phase 2 | ENG | Yogi quality dashboard | Refusal rate, latency, $/DAU, accept rate. | S-204; S-205 |  | todo | 1
S-211 | Phase 2 | ENG | 'Find people' search by interests | Up to 7 tags; opt-in discoverability. | S-105 |  | todo | 1
S-212 | Phase 2 | PROD | 7-interest profile slots | Bounded picker; swappable. | S-151 |  | todo | 1
S-213 | Phase 2 | ENG | Match scoring (92% MATCH) | Deterministic; tooltip explains. | S-211; S-212 |  | todo | 1
S-214 | Phase 2 | TRUST | Discovery rate-limits + safety | Anti-stalking; mutual mute. | S-211 |  | todo | 1
S-221 | Phase 2 | ENG | Survey creator (B2B) | 7-question micro-survey targeted by tags. | S-212 |  | todo | 1
S-222 | Phase 2 | PROD | Survey delivery in-app | Inbox card; capped at 1/day; skip respected. | S-221 |  | todo | 1
S-223 | Phase 2 | ENG | Survey results dashboard | k-anonymity ≥7 enforced. | S-221 |  | todo | 1
S-224 | Phase 2 | TRUST | Survey ethics + Terms update | Paid-survey clause; Privacy mirror. | S-221 |  | todo | 1
S-231 | Phase 2 | PROD | Business account onboarding | Company info, billing, tax ID; SI VAT + US EIN. | S-152 |  | todo | 1
S-232 | Phase 2 | PROD | Self-serve ad creator polish | Copy ≤70 words; 1 image; 7-tag targeting. | S-231; S-211 |  | todo | 1
S-233 | Phase 2 | PROD | Ad delivery slot in inbox | Sponsored card max 1/day; mute available. | S-232 |  | todo | 1
S-234 | Phase 2 | ENG | Ad auction + pricing | 2nd-price auction; settles <100 ms. | S-232 |  | todo | 1
S-235 | Phase 2 | ENG | Advertiser billing + invoices | Stripe + EU/SI VAT-MOSS aware. | S-231 |  | todo | 1
S-236 | Phase 2 | ENG | Advertiser analytics dashboard | Impressions/CTR/conv by tag+region; CSV export. | S-233 |  | todo | 1
S-237 | Phase 2 | TRUST | Ad policy + review queue | Manual review first 7 ads/advertiser; SLA 24h. | S-232 |  | todo | 1
S-238 | Phase 2 | TRUST | Ad transparency page (DSA) | Public archive; CSV download. | S-233 |  | todo | 1
S-241 | Phase 2 | PROD | Pro tier: raise the caps | 30 contacts, last-30 retention, 140-word msgs. | S-115; S-116; S-111 |  | todo | 1
S-242 | Phase 2 | PROD | Business tier: ads + Yogi pro | Tier check on each surface. | S-231 |  | todo | 1
S-243 | Phase 2 | ENG | Stripe checkout + sub mgmt | Portal; webhooks idempotent. | S-152 |  | todo | 1
S-244 | Phase 2 | TRUST | EU 14-day cancellation | Waiver to start digital service; refund flow. | S-243 |  | todo | 1
S-245 | Phase 2 | ENG | Tax handling (US states + EU VAT) | Stripe Tax; SI VAT; advisor review. | S-243 |  | todo | 1
S-246 | Phase 2 | PROD | Promo / referral system | Refer 7 → 7 days Pro free; abuse caps. | S-243 |  | todo | 1
S-247 | Phase 2 | PROD | Phase 2 launch checklist + flip | Flip Pro/Business/Ads/Yogi public; status green 24h. | S-241..S-246; S-208; S-237 |  | todo | 1
S-251 | Phase 2 | ENG | A/B test framework | Flag-based; stat-sig calc. | S-186 |  | todo | 1
S-252 | Phase 2 | ENG | Cohort analytics D1/D7/D30 | Wired to /pitch. | S-158 |  | todo | 1
S-253 | Phase 2 | PROD | Onboarding funnel optimization | Top-3 drop-off; ship 3 fixes. | S-251; S-252 |  | todo | 1
S-254 | Phase 2 | ENG | i18n scaffolding (EN/SI/ES/DE/FR) | SI ships first; RTL-ready. | S-153 |  | todo | 1
S-255 | Phase 2 | BIZ | SI launch microsite + press | RTV/Delo/Finance briefed. | S-254; S-193 |  | todo | 1
S-256 | Phase 2 | PROD | Phase 2 retro + Phase 3 readiness | 30-day retro; Phase 3 unblocked. | S-247 |  | todo | 1
S-301 | Phase 3 | BIZ | BaaS / EMI partner shortlist | 5 EU + 3 US partners; pricing & lead-time doc. | S-247 |  | todo | 1
S-302 | Phase 3 | BIZ | Partner selection + term sheet | Signed term sheet in data room. | S-301 |  | todo | 1
S-303 | Phase 3 | TRUST | KYC vendor selection | Sandbox connected; tested in 3 EU + US. | S-302 |  | todo | 1
S-304 | Phase 3 | TRUST | AML / sanctions screening | OFAC/EU/UN screening; FP resolution. | S-303 |  | todo | 1
S-305 | Phase 3 | TRUST | PSD2 / SCA compliance design | Biometric SCA for >€30; partner sign-off. | S-302 |  | todo | 1
S-306 | Phase 3 | TRUST | VAP Terms + fee schedule | Terms §14; lawyer-reviewed; behind flag. | S-305 |  | todo | 1
S-311 | Phase 3 | PROD | Wallet entry point in profile | Hidden behind 'vap' flag. | S-186; S-306 |  | todo | 1
S-312 | Phase 3 | PROD | Wallet onboarding (KYC handoff) | Decline reasons surfaced cleanly. | S-303; S-311 |  | todo | 1
S-313 | Phase 3 | PROD | Wallet home: balance + last 7 tx | Pull-to-refresh; stale-state CTA. | S-312 |  | todo | 1
S-314 | Phase 3 | ENG | Top-up via card / SEPA | Apple/Google Pay + SEPA; sandbox passes. | S-313 |  | todo | 1
S-315 | Phase 3 | ENG | Withdraw to bank | Cooldown + 2FA on first; SEPA. | S-313 |  | todo | 1
S-316 | Phase 3 | PROD | Statements + receipts | Monthly PDF; per-tx receipt. | S-313 |  | todo | 1
S-321 | Phase 3 | ENG | Virtual MasterCard issuance | PAN biometric-gated; Apple/Google Wallet. | S-313 |  | todo | 1
S-322 | Phase 3 | PROD | Card controls | Freeze, daily limit, region whitelist. | S-321 |  | todo | 1
S-323 | Phase 3 | ENG | 3DS / SCA push challenges | Challenge → approve <7 s p95. | S-321; S-305 |  | todo | 1
S-324 | Phase 3 | TRUST | Card disputes flow | Self-serve; partner SLA tracked. | S-321 |  | todo | 1
S-331 | Phase 3 | PROD | P2P transfer to a contact | 'Send €' from thread; 7 P2P/day on free wallet. | S-313 |  | todo | 1
S-332 | Phase 3 | PROD | Request money from contact | 'Request €' inline; 7-day expiry. | S-331 |  | todo | 1
S-333 | Phase 3 | PROD | Split bill (up to 7 people) | Auto-balance; remainder to initiator. | S-331 |  | todo | 1
S-334 | Phase 3 | ENG | Merchant pay (QR / link) | Sandbox merchant flow works. | S-321 |  | todo | 1
S-335 | Phase 3 | PROD | Cashback / promo credits | Wallet balance credits; promo expiry. | S-333 |  | todo | 1
S-341 | Phase 3 | PROD | Closed beta to 700 wallets | Whitelist; predefined KPIs. | S-321; S-331 |  | todo | 1
S-342 | Phase 3 | TRUST | Fraud monitoring | Velocity, device-binding, geo-velocity. | S-341 |  | todo | 1
S-343 | Phase 3 | PROD | CS tooling for VAP | Read-only wallet view (no PAN); 2 agents trained. | S-341 |  | todo | 1
S-344 | Phase 3 | PROD | Phase 3 PUBLIC LAUNCH | Flip flag for eligible regions; status green 7d. | S-341..S-343 |  | todo | 1
S-345 | Phase 3 | BIZ | Phase 3 retro + Series A readiness | Refreshed deck v2 in data room. | S-344 |  | todo | 1
B-001 | Business | BIZ | Pick legal home (US C-corp + SI sub) | Decision memo signed by Paul + Joze. | — |  | todo | 1
B-002 | Business | BIZ | 50/50 cap-table draft | ESOP 10%; 4y/1y vest. | B-001 |  | todo | 1
B-003 | Business | BIZ | Engage formation counsel (US + SI) | Engagement letters signed. | B-001 |  | todo | 1
B-004 | Business | BIZ | IP assignment from founders to NewCo | Signed assignments stored. | B-003 |  | todo | 1
B-005 | Business | BIZ | Trademark search + filing (US/EU/SI) | 3-jurisdiction search; priority filed. | B-003 |  | todo | 1
B-006 | Business | BIZ | Define €1M angel offer | Two options: SAFE €10M cap vs Series Seed €8M pre. | B-002 |  | todo | 1
B-007 | Business | BIZ | Investor data-room build | Mirror /pitch privately; NDA-gated extras. | S-158; B-002; B-006 |  | todo | 1
B-008 | Business | BIZ | Pitch deck v2 (12 slides) | Problem → Rule of 7 → traction → roadmap → ask. | B-007 |  | todo | 1
B-009 | Business | BIZ | Boscarol-track outreach (Slovenia) | Intro mapping; SI script; first ask sent. | B-008 |  | todo | 1
B-010 | Business | BIZ | Diversify: 7 SI/EU + 7 US angels | 14-name target list with rationale. | B-008 |  | todo | 1
B-011 | Business | BIZ | Capital plan (use of funds, by quarter) | Quarterly burn vs milestones; 18-mo runway. | B-006 |  | todo | 1
B-012 | Business | BIZ | Close the round | Sign + wire; cap-table updated; embargoed announcement. | B-009 or B-010 |  | todo | 1
S-009 | Sprint 0 | TRUST | Contact email migration to info@copyme1.com | Replace interactiveintel@gmail.com everywhere; DNS+SPF+DKIM+DMARC; old gmail kept as 90-day alias. | — |  | todo | 1 |  |  |  | NEW per Feedback 3 (2026-05-10) — confirm copyme1.com is registered first
S-010 | Sprint 0 | PROD | Hero: add 'Your World's chart of Communication' as H2 | Below H1 'Communication That Matters' insert H2; OG regenerated. | S-001 |  | todo | 1 |  |  |  | NEW per Feedback 3 (2026-05-10)
B-013 | Business | BIZ | Use of proceeds — €1M breakdown | Per-line use of funds by category and quarter, summing exactly to €1M; tied to milestones. | B-006 |  | todo | 1 |  |  |  | NEW per Feedback 3 — Joze asked 'Show use of proceeds'
B-014 | Business | BIZ | Additional investor target list (≥21 names) | 7 SI/EU + 7 US + 7 strategic/corporate; rationale + intro path; ranked. | B-008 |  | todo | 1 |  |  |  | NEW per Feedback 3 — Joze asked 'Search for other potential targets'
B-015 | Business | BIZ | Timeline-to-launch communique for Joze | 1-page public-shareable timeline with G0..G3 gates; md + pdf. | — |  | todo | 1 |  |  |  | NEW per Feedback 3 — Joze asked for time estimation
B-016 | Business | TRUST | Definition of 'Customer-ready' gate | Written definition (Functional/Trust/Ops/Regional bars + sign-off matrix). | — |  | todo | 1 |  |  |  | NEW per Feedback 3 — Joze asked 'Where is the point where clients can apply'

## Dashboard
CopyMe Sprint Dashboard
Overall progress |  | By Phase |  |  |  | By Workstream
Total sprints | 161 | Phase | Total | Done | % complete | Workstream | Total | Done | % complete
Done | 0 | Sprint 0 | 10 | 0 | 0% | ENG | 62 | 0 | 0%
In progress | 0 | Phase 1 | 72 | 0 | 0% | PROD | 44 | 0 | 0%
Blocked | 0 | Phase 2 | 37 | 0 | 0% | TRUST | 34 | 0 | 0%
To do | 161 | Phase 3 | 26 | 0 | 0% | BIZ | 21 | 0 | 0%
% complete | 0% | Business | 16 | 0 | 0%
Hours remaining (est) | 161

## Joze Feedback
# | Date received | From | Topic | Joze's request (verbatim or paraphrase) | Closed by sprint(s) | Status
1 | 2026-05-07 | Jože | Hero copy | First contact when opening CopyMe page is too dense. Rule of 7 should be felt, not enumerated. Move details to T&C. | S-001, S-002, S-003 | todo
2 | 2026-05-07 | Jože | Hero copy | New main headline: 'Your World's chart of Communication'. | S-001 | todo
3 | 2026-05-07 | Jože | Hero copy | Subhead: 'Rule of 7 — A revolutionary constraint system that replaces noise with meaning. Less is more, giving meaning to messages. Infinite impact.' | S-002 | todo
4 | 2026-05-07 | Jože | Terms | Rule-of-7 details (70 words, 7 contacts, last-7 retention) belong in T&C, not on landing. | S-003 | todo
5 | 2026-05-07 | Jože | Terms | Suspension wording: 'Accounts that break these rules may be suspended' (and fix typo 'suspened'). | S-004 | todo
6 | 2026-05-07 | Jože | Logo | Like the logo — drop the 'Rule of 7' script underneath. | S-005 | todo
7 | 2026-05-07 | Jože | Logo | Could we add a small globe with a man in front, as on the original paper? | S-006 | todo
8 | 2026-05-07 | Jože | Phone auth | Add country code +386 (Slovenia) so we can test on phones. | S-007 | todo
9 | 2026-05-07 | Jože | QA | When technically ready, test on the phones and communication. | S-008 | todo
10 | 2026-05-10 | Jože | Hero correction | Keep 'Communication That Matters' as H1 (was never meant to be removed); 'Your World's chart of Communication' is the H2 below it. | S-001 (corrected), S-010 | todo
11 | 2026-05-10 | Jože | Contact email | Change interactiveintel@gmail.com to info@copyme1.com everywhere. | S-009 | todo
12 | 2026-05-10 | Jože | Investors | Search for other potential investment targets and provide a list (beyond Boscarol). | B-014 | todo
13 | 2026-05-10 | Jože | Timeline | Establish a time estimation for when app is technically ready to run and grow. | B-015 | todo
14 | 2026-05-10 | Jože | Launch gate | Where is the point where clients can apply (define customer-ready). | B-016 | todo
15 | 2026-05-10 | Jože | Use of funds | Show use of proceeds for the €1M. | B-013 | todo

## Feedback 3 Deltas
Feedback 3 (2026-05-10) — what's new
5 new asks beyond what Feedback 2 already covered.
Ask | New sprint(s) | Target close | Status
Hero — keep 'Communication That Matters'; add H2 | S-001 (corrected), S-010 | 2026-05-12 | todo
Contact email → info@copyme1.com | S-009 | 2026-05-12 | todo
Use of proceeds for €1M | B-013 | 2026-05-29 | todo
Additional investor target list (≥21) | B-014 | 2026-05-29 | todo
Timeline-to-launch communique | B-015 | 2026-05-13 | todo
Definition of 'Customer-ready' | B-016 | 2026-05-13 | todo

## Capital Plan
Capital Plan — €1M angel raise (placeholder)
Note: Refine in sprint B-011. All figures in EUR.
Quarter | Eng salaries | Infra/Vercel/SMS/AI | Legal/Compliance | Marketing/PR | Other | Quarter total | Cumulative spend | Remaining of €1M
Q3 2026 | 60000 | 12000 | 8000 | 25000 | 5000 | 110000 | 110000 | 890000
Q4 2026 | 75000 | 15000 | 5000 | 40000 | 5000 | 140000 | 250000 | 750000
Q1 2027 | 90000 | 20000 | 4000 | 60000 | 5000 | 179000 | 429000 | 571000
Q2 2027 | 90000 | 25000 | 4000 | 60000 | 5000 | 184000 | 613000 | 387000
Q3 2027 | 95000 | 30000 | 4000 | 70000 | 5000 | 204000 | 817000 | 183000
Q4 2027 | 95000 | 35000 | 4000 | 80000 | 5000 | 219000 | 1036000 | -36000
TOTAL | 505000 | 137000 | 29000 | 335000 | 30000 | 1036000